## Sheet1
Week | Tasks
2018-02-26 | User Story List. Choose a Source Code Control System and install for entire team, project lead to check a test file in and the members should demonstrate check out, modify and check in knowledge Choose bug tracker system they are going to use. Each member demonstrates use of filing a bug report. TAs ask each team member to demonstrate use of the SCCS and the bug tracker to make sure they are all on board. TAs verify that you have been given access to their source code in Git or whatever system they are using. TAs inspect Meeting Minutes document and record absences.
2018-03-05 | The team will play planning poker. The TA will introduce at least 3 new features into the User Story List. Each team member will have a User Story Card. The top will have the user story description and the bottom will have the time estimate needed to implement the User Story AND the assumptions he/she made for that estimate. The Project Lead should take the average of the time estimates presented. There should be a debate about the numbers if needed. The time estimate and assumptions should be captured by the Project Lead in the Appendix of the Product Requirements Document the template of which is in Canvas. TAs inspect Meeting Minutes document and record absences.
2018-03-12 | TAs finalize the User Story list. Discuss the time estimates, drop some stories if needed, TAs use research of estimates to drive this. TAs inspect Meeting Minutes document and record absences.
2018-03-26 | TAs review of the following: 1. Software Requirements Document (Template in Canvas) 2. High Level Design Document (Template in canvas TBD) 3. Configuration Management Plan (Template in Canvas TBD) 4. Sprint Plan on a weekly basis.(Template in Canvas TBD) Quickly eyeball of all documents. If there are 4 members in the group, pick 4 sections, assign it to each member and ask them to explain the contents. TAs inspect Meeting Minutes document and record absences.
2018-03-27 | First Demonstration of Requirements, Design, Plans 1. Submit all documents 2. Prepare slide set 2 per document for presentation TAs inspect Meeting Minutes document and record absences.
2018-04-02 | TAs perform scrum per weekly sprint plan a. Review tasks completed b. Review bug list c. Prepare a list of proposed design changes etc and get it approved by Customer d. TAs inspect Meeting Minutes document and record absences.
2018-04-09 | TAs perform scrum per weekly sprint plan a. Review tasks completed b. Review bug list c. Prepare a list of proposed design changes etc and get it approved by Customer d. d. Prepare questions for Apr 19 deliverable, see below cell for list and get ready e.TAs inspect Meeting Minutes document and record absences.
2018-04-16 | TAs perform scrum per weekly sprint plan a. Review tasks completed b. Review bug list c. Prepare a list of proposed design changes etc and get it approved by Customer d.TAs inspect Meeting Minutes document and record absences.
2018-04-23 | Customer review of the following: 1. Unit Test Plan Document (Template in Canvas TBD) 2. System Test Plan Document (Template in Canvas TBD) 3. Performance Document (Template in Canvas TBD) 4. Unit Test Report Document (Template in Canvas TBD) 5. System Test Report Document (Template in Canvas TBD) 6. Performance Test Report (Template in Canvas TBD) Quickly eyeball of all documents. If there are 4 members in the group, pick 4 sections, assign it to each member and ask them to explain the contents. 7.TAs inspect Meeting Minutes document and record absences.
2018-04-26 | Demonstration #2 TAs inspect Meeting Minutes document and record absences.
2018-04-30 | TAs perform scrum per weekly sprint plan a. Review tasks completed b. Review bug list c. Prepare a list of proposed design changes etc and get it approved by Customer
2018-05-07 | TAs perform scrum reviews the following: 1. Unit Test Report 2. System Test Report 3. Performance Report Quickly eyeball of all documents. If there are 4 members in the group, pick 4 sections, assign it to each member and ask them to explain the contents. 4. Group should demo the project and the customer must appropriately use the Acceptannce Plan list and tick off completed User Stories 5.TAs inspect Meeting Minutes document and record absences.
2018-05-10 | Final Demonstration TAs inspect Meeting Minutes document and record absences.